## Slide 1: INTERNSHIP 2024 SOLID PROPULSION
WEEK 6 PROGRESS REPORT

## Slide 2: SOLID PROPULSION N3.5 GANTT CHART
https://docs.google.com/spreadsheets/d/1VY4SawCWrPL2GLTEFuGG4h4JeNr9AABdcgp3iwnV6gs/edit?usp=drivesdk

## Slide 3: SIXTH WEEK’S OBJECTIVES
Analysis of the static test
Machining of nozzles
Machining of bulk heads
Purchase of Materials
Cooking grains
Design of casting tool

## Slide 4: TASKS COMPLETED
  Motor disassembly and assessment.
  Static test analysis.
  Redesigned casting moulds.
  Cooked 3 grains
  Procured some materials.
  Fabricated 4 nozzles.
  Reviewed compression moulding machine upgrade.

## Slide 5: MOTOR ASSESSMENT
Nozzle O-rings destroyed
Bulkhead O-rings intact
All metallic components intact

## Slide 6: STATIC TEST ANALYSIS
Approximated burn time: 1.5 seconds
Data points: 30
Sampling time =
    =
      = 0.05 Seconds
FUTURE IMPROVEMENTS
Update code on the time stamp
Integrate pressure sensor

## Slide 7: STATIC TEST ANALYSIS
Burn time: 1.5 seconds.
Given thrust: 160kgf
The rocket motor based on the calculated impulse
of 1220.74Ns lies within class J (640-1280Ns) of SRM
Total Impulse = Area under the graph
      = Δ) =
      =1220.74Ns

## Slide 8: SIMULATED THRUST CURVE
IMPULSE = 2103.6Ns

## Slide 9: STAtic test analysis
OUR THRUST CURVE

## Slide 10: MACHINING BULK HEADS

## Slide 11: REDESIGNING CASTING MOULDS

## Slide 12: COOKING OF GRAINS

## Slide 13: MATERIALS PROCUREMENT
More materials to be procured beginning of next week
MILD STEEL SOLID SHAFT
BORING TOOL

## Slide 14: NOZZLES FABRICATION
4 NOZZLES BEGAN FABRICATION

## Slide 15: CHALLENGES
 | CHALLENGES
1 | Complications in purchasing and transportation of the SCH40 tube

## Slide 16: NEXT WEEKS TASKS
NO. | TASK
1 | Nozzle fabrication progression
2 | Ignition circuit development
3 | Research and redesign of the casting mould progression
4. | Cooking of grains
5. | Machining of more bulkheads
6 | Test stand repair
7 | Static test integrating with the airframe

## Slide 17: THANK YOU